## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Big Mart Sales prediction |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | AP SHAH INSTITUTE OF TECHNOLOGY(Information Technology)
PROJECT GUIDE |  | Prof.Rujata Chaudhari |  |  |  |  | DATE | [6 empty] | 2023-04-13
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PERCENTAGE OF TASK COMPLETE | PHASE ONE | [49 empty] | PHASE TWO
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 | [7 empty] | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Group formation and Topic finalization. Identifying the scope and objectives of the Mini Project | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 13/01/23 | 18/01/23 | 2 | 100% | bar: WEEK 1 M to WEEK 2 F
1.2 | Identifying the functionalities of the Mini Project | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 20/01/23 | 26/01/23 | 2 | 100%
1.3 | Discussing the ML Algorithm | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 29/01/23 | 2023-03-02 | 2 | 100% | bar: WEEK 5 M to WEEK 6 F
1.4 | Designing the Graphical User Interface(GUI) | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 2023-02-04 | 2023-02-10 | 3 | 100% | bar: WEEK 7 M to WEEK 9 F
1.5 | Presentation I | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 17/02/23 | 17/02/23 | 1 | 100%
2 | Project Design and Implementation
2.1 | Detail ML Algorithm implementation | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur | 20/02/23 | 28/02/23 | 1 | 100% | bar: WEEK 10 M to WEEK 11 F
2.2 | Integration of GUI with ML Algorithm code | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 2023-03-03 | 2023-10-03 | 1 | 100% | bar: WEEK 11 M to WEEK 12 F
2.3 | Report Writing | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 14/03/23 | 21/03/23 | 1 | 100%
2.4 | Presentation II | Madhur Dukhande,Manashree Chavan,Aryan Amin, Mayur Jain | 13/04/23 | 13/04/23 | 2 | 100% | bar: WEEK 13 M to WEEK 14 F